## Teams
Titre | Description | Fichier | Personne | Date prévue | Date de livraison | Statuts | Remarks
Simulation Environment Development |  |  | Sidy and Zad | 10/10/2025 00:00 | 10/10/2025 00:00
Install and learn to use ROS |  |  | Zad and Madiara | 10/10/2025 00:00 | 10/10/2025 00:00
Strategy |  |  | All members | 17/10/2025 00:00 | 17/10/2025 00:00
List of required electrical appliances |  |  | Madiara | 22/10/2025 00:00 | 22/10/2025 00:00
2D Simulation of route(s) |  |  | Sidy and Zad | 2025-10-30
Dribbler design |  |  | Zhonghe and Samsaam | 30/10/2025 00:00
Robot design |  |  | Zhonghe and Samsaam | 07/11/2025 00:00
Purchase/Select Electrical Components |  |  | Madiara and Sidy | 2025-11-07
Cursor Design |  |  | Zhonghe and Samsaam | 2025-11-17
Camera Command Programming |  |  | Sidy and Zad | 14/11/2025 00:00
Movement Command Programming |  |  | Sidy and Zad | 21/11/2025 00:00
Print and assembly the dribbler |  |  | Madiara | 21/11/2025 00:00
Dribbler Programming |  |  | Sidy and Zad | 2025-12-15
Curons programming |  |  | Sidy and Zad | 2025-12-28
Simulation |  |  | Sidy and Zad | 09/01/2026 00:00
Test tasks |  |  | All members | 16/01/2026 00:00
Final presentation |  |  | All members | 23/01/2026 00:00
Probant |  |  | Madiara and Zhonghe | All time
Presentation |  |  | All members | All time
Meeting reports |  |  | All members | All time

## Zhonghe
Task | Description | Fichier | Starting Date | Expected End date | Actual End Date | Statuts | Remarks
Dribbler design
Robot design |  |  | 20/10/2025 0:00 | 31/10/2025
Cursor Design |  |  | 2025-11-11 | 17/11/2025
Print and assembly the dribbler
Test tasks
Final presentation
Probant
Presentation
Meeting reports

## Samsaam
Task | Description | Fichier | Starting Date | Expected End date | Actual End Date | Statuts | Remarks
Dribbler design |  |  | 2025-10-01 | 2025-10-31 | 2025-11-01 |  | I amde the first prototype
Robot Case design |  |  | 2025-10-10 | 2025-11-02 |  |  | Me and Zhonge are working on it.
Printing of CAD models: Dribbler |  |  | 2025-11-03 | 2025-11-10
Fabricate Robot Case |  |  | 2025-11-04 | 2025-11-17
Complete the Assembly of Robot Body |  |  | 2025-11-05
Embedded the eletronics on the Robot Body |  |  | 2025-11-18

## Sidy
Task | Description | Fichier | Starting Date | Expected End date | Actual End Date | Status | Remarks
Simulation Environment Development |  |  | 2025-07-10 | 17/10/2025 | 15/10/2025
Install and learn to use ROS |  |  | 2025-07-10 | 2025-11-02
Strategy |  |  | 2025-11-17
2D Simulation of route(s) |  |  | 2025-12-15
Camera Command Programming |  |  | 16/10/2025 |  | 16/10/2025
Movement Command Programming
Dribbler Programming
Curons programming
Simulation
Test tasks

## Zad
Task | Description | Fichier | Starting Date | Expected End date | Actual End Date | Statuts | Remarks
Simulation Environment Development |  |  | 2025-10-10 | 31
Install and learn to use ROS |  |  | 07/11/2025 00:00 | 2025-11-02
Strategy |  |  | 2025-11-17
List of required electrical appliances |  |  | 21/11/2025 00:00
2D Simulation of route(s) |  |  | 2025-12-15
Cursor Design |  |  | 2025-12-16
Camera Command Programming |  |  | 2025-12-17
Movement Command Programming |  |  | 2025-12-18
Dribbler Programming |  |  | 2025-12-19
Curons programming |  |  | 2025-12-20
Simulation |  |  | 2025-12-21
Test tasks |  |  | 2025-12-22
Final presentation |  |  | 2025-12-23
Presentation |  |  | 2025-12-24
Meeting reports |  |  | 2025-12-25

## Madiara
Task | Description | Fichier | Starting Date | Expected End date | Actual End Date | Statuts | Remarks
Simulation Environment Development |  |  | 2025-10-10 | 31
Strategy |  |  | 2025-11-17
List of required electrical appliances |  |  | 21/11/2025 00:00 | 2025-02-11
2D Simulation of route(s) |  |  | 2025-12-15
Dribbler design
Robot design |  |  | 20/10/2025 0:00 | 31/10/2025 | 29/10/2025 |  | QIAO
Purchase/Select Electrical Components |  |  |  | 24/11/2025
Cursor Design
Camera Command Programming
Movement Command Programming
Print and assembly the dribbler
Dribbler Programming
Curons programming
Simulation
Test tasks
Final presentation
Probant
Presentation
Meeting reports